## Sheet1
The game is designed in four classes namely , UserInterface.java, ArtificialIntelligence.java, GameDesign.java and Board.java.
This Document provides the Code Inspection, Design Inspection and Unit Inspection for these four classes.
1 | Product | Battleship: Design Inspection Log for Board.java
| Date | 2013-09-11
| Author | Udbhav Sahai
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | David Zinn
| Defect # | Description | Severity | How Corrected
| 1 | The user must not be allowed to attempt to hit a spot on the field more than once | 2 | A check is implemented to see if the spot has already been hit before using an array that will store all hits
| 2 | The user must not be able to stack ships | 2 | If the current location already has a ship placed in the grid on the Board object, then it will return an error
| 3 | The position of the users' ships all must occupy a unique space (no overlapping) | 2 | A check will be implemented to see if the location already has a ship on it on the Board object
| 4 | Counting the hits on the ships based on whose ships are being hit | 2 | Global counters were added to the Board object to ensure that individual tracking is performed
2 | Product | Battleship: Code Inspection Log for Board.java
| Date | 2013-09-11
| Author | Udbhav Sahai
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | David Zinn
| Defect # | Description | Severity | How Corrected
| 5 | User should place a ship in area that has proper space for it. The ship will not wrap to next tile | 2 | By putting checks in Board.java that do not allow the starting and ending x and y coordinate to go beyond a certain value
| 6 | Ships are being hit in the order they were set in | 2 | A return value is generated that will inform the Board object which ship is hit, so that the correct ship is hit
| 7 | Placing ships wrongly | 2 | The horizontal and vertical coordinates are checked to see if the x- and y-coordinates are valid
| 8 | Ship counts should not go into negative | 2 | When the ship count is 0, it wil be validated by the array of coordinates which records all shots
| Product | Battleship: Unit Inspection for Board.java
| Date | 2013-09-11
| Author | Udbhav Sahai
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | David Zinn
3 | Defect # | Description | Severity | How Corrected
| 9 | Generation of grid with panel after "PLAY!" button is pressed | 1 | The runnable is placed as a private class within the User Interface to avoid passing the game data to another class
| 10 | Incorrect reflection of placements and hits/misses on the board object | 2 | Board.java creates its own grid independent of UserInterface.java and tracks all hits in an encapsulated class
| Product | BattleShip: Design Inspection for UserInterface.java
| Date | 2013-09-11
| Author | Tejesh Priyatham Kalidindi
| Moderators | David Zinn
| Inspectors | Kamraan Pirwani, Kritin Gokharu, Udbhav Sahai
| Recorder (Secretary) | Mikhail Kim
| Defect # | Description | Severity | How Corrected
| 11 | There is no back button when the user enters the game to go back to the main menu. | 3 | Added a back button which pauses and goes to the Main Screen
| 12 | The user must not be allowed to attempt to hit a spot on the field more than once. | 2 | Once a user hits a spot that spot is replaced by a non-clickable Jpanel to avoid repeated hits.
| 13 | UI freezes in certain scenarios. | 3 | Created a new runnable for the UI. To keep the processes separate.
| 14 | Cannot Mute the Background Music | 3 | Added a Mute Button
4 | Product | BattleShip: Code Inspection for UserInterface.java
| Date | 2013-09-11
| Author | Tejesh Priyatham Kalidindi
| Moderators | Mikhail Kim
| Inspectors | Kamraan Pirwani, Kritin Gokharu, Udbhav Sahai
| Recorder (Secretary) | David Zinn
| Defect # | Description | Severity | How Corrected
| 15 | High Scores are not in Chronological Order. | 3 | Added a sort function of the data Structure before Displayed on the screen
| 16 | When the game ends, there is no way to go back to the main screen | 2 | Put a sleep timer of 5 seconds on whose completion the UI goes back to the Main Menu
| 17 | The buttons of the Game were unevenly sized and shaped | 3 | Added a UI.pack() command to dynamically size them to be a proper shape.
| 18 | Image location error -- when initialy we had an absolute path it gave errors and would crash as it couldn’t find the Gamescreen image | 1 | We used an URL object to get the pathToImage dynamically instead of having a filepath.
| Product | BattleShip: Unit Inspection for UserInterface.java
| Date | 2013-09-11
| Author | Tejesh Priyatham Kalidindi
| Moderators | Mikhail Kim
5 | Inspectors | Kritin Gokharu, Udbhav Sahai
| Recorder (Secretary) | Kamraan Pirwani
| Defect # | Description | Severity | How Corrected
| 19 | The Screen doesn’t refresh to a new set of Objectson the screen after their instantiation. | 2 | Added a validate UI after every change made to screen to keep it updated to the latest change.
| 20 | Player name doesn’t change when changed during a game. | 3 | Added a new condition to change the static name object and validate the Jlabel on the UI on the game screen.
| Product | Battleship: Design Inspection for GameDesign.java
| Date | 2013-09-11
| Author | Kritin Gokharu, Mikhail Kim
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | Tejesh Priyatham, Mikhail Kim
| Defect # | Description | Severity | How Corrected
| 21 | A user cannot find a game hosted by another user | 2 | Add field for direct connect( by specifying the host IP address and port) to enable connections anywhere on the internet
| 22 | A user cannot host a game successfully | 2 | There were issues with binding a port to a number below 1024 as they are reserved for super users and administrators. Fixed by changing the port to a valid port
| 23 | Upon termination of the game for various reasons, the game is not saved | 3 | Autosave the game after every move
| Product | Battleship: Code Inspection for GameDesign.java
| Date | 2013-09-11
| Author | Kritin Gokharu
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | Tejesh Priyatham, Mikhail Kim
| Defect # | Description | Severity | How Corrected
| 24 | There was a clash while using the MVC design pattern | 1 | We had to transfer controller ownership from User Interface to Game Design
| 25 | Anyone service can currently connect to our server | 1 | There needs to be validation between client and server
| 26 | The networking calls block the UI | 3 | Move networking tasks to a separate thread
| Product | Battleship: Unit Inspection for GameDesign.java
| Date | 2013-09-11
| Author | Kritin Gokharu, Mikhail Kim
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | Tejesh Priyatham, Mikhail Kim
| Defect # | Description | Severity | How Corrected
| 27 | Saved games are not properly loaded back into memory | 2 | We were using an inefficient method for saving the state of the game. Fixed by serializing the classes and saving to a data file
| 28 | The save game button does not output a valid object | 2 | We were using an inefficient method for saving the state of the game. Fixed by serializing the classes and saving to a data file
| 29 | The user cannot select which saved game to load | 2 | A dialogue box prompts the user to select the appropriate game save
| Product | Battleship: Design Inspection for AIPlayer.java
| Date | 2013-09-11
| Author | Kamran Pirwani
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | Tejesh Priyatham, Mikhail Kim
| Defect # | Description | Severity | How Corrected
| 30 | AI cannot send information correctly - Xcoordinate and Ycoordinate | 2 | Data sent to AI board is checked before being sent
| 31 | Stack overflow because all ships are already sunk and AI still plays | 1 | The checkAll() function is called to ensure that end of game has been reached
| 32 | Constructor in AIPlayer.java is unable to receive the call to generate a hit | 1 | Create a constructor to be able to read in the query for a hit to be generated
| Product | Battleship: Code Inspection for AIPlayer.java
| Date | 2013-09-11
| Author | Kamran Pirwani
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | Tejesh Priyatham, Mikhail Kim
| Defect # | Description | Severity | How Corrected
| 33 | Incorrect Random coordinate generator | 2 | Lower and upper bounds were placed so that it would generate in a given range
| 34 | Random generator stops generating numbers | 1 | The generator is removed from the loop and placed in a function that is called everytime the constructor is called
| 35 | Incorrect passing of data to Board.java due to incorrect parameters | 1 | Parameters are placed in the right order and of the right data type to ensure data is passed correctly
| Product | Battleship: Unit Inspection for AIPlayer.java
| Date | 2013-09-11
| Author | Kamran Pirwani, Mikhail Kim
| Moderators | Mikhail Kim
| Inspectors | Tejesh Priyatham, Kritin Gokharu, Kamran Pirwani
| Recorder (Secretary) | Tejesh Priyatham, Mikhail Kim
| Defect # | Description | Severity | How Corrected
| 36 | Passing of values crashes application because it cannot find AI board | 1 | Check to see if board is created before passing values
| 37 | Deletes from the wrong board | 2 | Ensure that correct Board object is called for deletion process